## Sheet1
General guideline | Faculty led Study Abroad Programs | Program Leader | Business Manager | Study Abroad | Bursar | Student
12-18 months | Develop a program | X
12 months | Develop preliminary budget | X | X
9 months | Submit Proposal | X
9 months | Approve Departmental Program |  |  | X
9 months | Establish study abroad course number (SA course number) |  |  | X
9 months | Create Web page |  |  | X
9 months | Update web page with program information - start student recruitment | X
3-9 months | Enroll in program on study abroad site |  |  |  |  | X
3-9 months | Monitor student enrollments, edit student status and track document submissions | X
6 months | Establish program account and validate account set up |  | X
5 months | Prepare/submit Rate Request and Cancellation Policy, establish deadline for SA deposit | X | X
5 months | Approve Rate Request |  |  | X
5 months | Add cancellation policy to program leader page for student to complete | X
5 months | Check visa requirements | X
3 months | Submit cost sheets to DFA |  |  | X
Rolling as paid | Apply deposits to student accounts |  |  |  | X
3 months | Determine program viability (based on student enrollments) | X | X
2-3 months | Enter student registrations in BANNER (during open registration) |  |  | X
2 months (rolling) | Invoice student for program fees |  |  |  | X
2 months | Pay program fees through Bursar account |  |  |  |  | X
2 months (rolling as students registered) | Transfer program fee to department account |  |  |  | X
2 months | Complete travel requirements in Concur, establish credit card and determine limits | X | X
2-5 months (early spring) | Attend Faculty/Staff Health and Safety Orientation | X
2 months | Conduct student pre-departure meetings | X |  | X
2 month | Ensure mandatory forms submitted by students | X
1-2 months | Review course roster and program accounts | X | X
1-2 months (final roster) | Order emergency medical coverage for participating students |  | X
1-2 months (final roster) | Distribute insurance cards to students (once received from Risk Mgmt.) | X
1-2 months | Complete online pre-departure orientation |  |  |  |  | X
1 month | Submit program leader forms to study abroad (final itinerary, emerg form, STEP reg) | X
Post - 2 weeks | Submit grades to study abroad via program leader page | X
Post - rolling - 2 weeks | Submit grades to Registrar for posting |  |  | X
Post - 1 month | Evaluate program | X |  | X |  | X
Post - 1 month | Submit assesment data to CILMAR | X
Post - 1 month | Process program expenses and review expenditures | X | X
Post - 1 month | Evaluate account balance |  | X